## Sheet1
ID | Bug Title | Description | Priority | Status | Area | Notes
1 | User deletion counter not updating | Deleting users does not reduce competition count | High | Open | Backend
2 | Manual add users shows paid | Admin shows users as paid when manually added | High | Open | Payments/Admin
3 | Sponsor weight calculation unclear | Unclear how sponsor weighting works | High | Open | Logic
4 | Payment issues | Potential issue with payments | High | Open | Payments
5 | Slider size unclear | Need defined size for mobile and web sliders | Low | Open | UI/UX
6 | No fish image upload in admin when adding weight | Admin cannot upload fish images to competition | High | Open | Admin
7 | Contact form email change | Update contact email to Ian.justo@pegslam.com | Low | Open | Content
8 | Admin login issue | Bradley cannot log in | High | Open | Auth
9 | Sponsor link issue | Link incorrectly prefixed with pegslam.com | Medium | Open | Frontend
10 | Social media update | Replace Twitter with TikTok | Low | Open | Content/UI
11 | Phone number requirement | Make phone number mandatory and private | High | Open | Auth/Data
12 | Gallery not user-friendly | Gallery UX needs improvement | Medium | Open | UI/UX
13 | leader boards text | Leader board page seems a bit off with text coming out the box | Medium | Open | UI/UX